## Dashboard
PearCup Feature and User Story Status
Canonical tracker generated from current code after WDK/QVAC integration. Branch: main; commit: 84044b3; generated: 2026-07-02.
Metric | Value | Meaning | Current Gate | Result | Evidence | Next Action | Phase
Total stories | 70 | All code-grounded feature stories in User Stories. | Worktree | Clean | git status: main ahead 1 with no dirty files before workbook generation | Keep tracker committed after changes. | Baseline
Integrated stories | 70 | Rows whose Feature Status is Integrated. | Runtime tests | Passed | npm run check: 282/282 tests plus audit/checks | Manual user-story loop. | Baseline
Manual not run | 54 | Rows still awaiting manual behavior testing. | Kawaii syntax | Passed | All staged JS/CJS files parsed | Retest after each fix. | Manual Test
Manual passed/smoke | 16 | Rows with Passed or Passed (Smoke). | Browser smoke | Passed | Top nav screens active; no boot banner; no console errors | Deep workflow testing. | Manual Test
Open defects | 0 | Defects with Open or In Progress status. | Pear audit | Passed | 68 passed, 0 blocking, 0 warnings | Document every defect found. | Defects
Fixes awaiting retest | 0 | User stories or defects marked Retest Needed. | Integration commit | 84044b3 | Merged tested WDK/QVAC runtime into Kawaii app | Commit fixes and repeat gate. | Fix/Retest
P0 stories | 34 | Release-blocking stories and integrity gates. | Server | Running | Static preview at http://127.0.0.1:4175/ | Use for browser loop. | Manual Test
Stories needing fix | 0 | User stories marked Needs Fix. | Canonical workbook | Created | This workbook is the single tracker for feature status, test results, defects, fixes, and retests. | Fill Defect Log during testing. | Defects
Workflow | Owner | When | Action | Workbook Sheet | Done Signal | Risk If Skipped | Notes
1. Inventory | Codex | Now | Keep every feature represented by a user story and expected behavior. | User Stories | Story exists with code refs. | Untested features hide in plain sight. | Initial inventory complete from code and docs.
2. Test loop | Codex | Next | Execute each user story and log any error immediately. | User Stories, Defect Log, Test Runs | Manual Test Status updated. | Bugs become anecdotal instead of traceable. | Start with P0/P1 flows.
3. Fix loop | Codex | After defects | Patch logistical and UX defects with focused commits. | Defect Log | Fix Commit and Fix Status filled. | Fixes lose context. | Keep worktree clean between batches.
4. Retest loop | Codex | After fixes | Retest every affected behavior and update status. | User Stories, Defect Log | Retest Status passed or blocked. | Regressions slip through. | Repeat full gate after fixes.
5. Release gate | Codex/User | Before handoff | Run repo check, Kawaii syntax, browser smoke, and review open defects. | Dashboard, Test Runs | No open P0/P1 defects. | Unclear release confidence. | Current baseline is green.

## User Stories
Story ID | Area | User Story | Expected Behavior | Code / Selectors | Automation / Smoke Evidence | Manual Test Steps | Priority | Feature Status | Manual Test Status | Defect IDs | Fix Status | Retest Status | Notes
US-001 | Boot and Navigation | As a returning player, I can open PearCup without a runtime crash. | The app loads the Kawaii shell, initializes required modules, and shows a readable boot banner only if a required dependency is missing. | design/kawaii-app/index.html; design/kawaii-app/app.js: needModule, boot; module script tags | npm run check passed; browser smoke found no boot banner or console errors. | Open http://127.0.0.1:4175/, reload, verify title, shell, wallet chip, profile chip, and no PearCup boot error. | P0 | Integrated | Passed (Smoke) |  | None | Not Run | Current live tab passed on 2026-07-02.
US-002 | Boot and Navigation | As a player, I can move between Profile, Home, Bracket, Watch, and Games from the top nav. | Each top-nav button activates exactly one screen and leaves expected controls visible. | design/kawaii-app/index.html: .topnav buttons; design/kawaii-app/app.js: setView, bindViewButtons | Browser smoke clicked all top-nav screens successfully. | Click Profile, Home, Bracket, Watch, Games; verify each section receives is-active and expected controls render. | P0 | Integrated | Passed (Smoke) |  | None | Not Run | CTA buttons also share data-view and are intentionally excluded from top-nav uniqueness.
US-003 | Boot and Navigation | As a player, my app state survives reloads. | Profile, wallet, picks, room/game state, theme, and settings load from localStorage with safe fallback defaults. | design/kawaii-app/app.js: loadState, persist, STORAGE_KEY | Syntax covered; requires manual persistence pass. | Change username, team, theme, live setting, and a bracket draft; reload; verify values restore without duplicates or crashes. | P1 | Integrated | Not Run |  | None | Not Run
US-004 | Runtime Integration | As an operator, I can run in demo mode when live SDK packages are absent. | Runtime config falls back to demo adapters and reports demo/compliance locks without breaking user flows. | app/runtime-config.js; app/runtime-settings.js; design/kawaii-app/runtime-config.js; design/kawaii-app/app.js: integrationRuntime | npm run check: runtime-config/runtime-settings/adapters tests passed. | Open app without SDK globals; verify live readiness panels show demo status and gameplay/brackets remain usable in demo mode. | P0 | Integrated | Not Run |  | None | Not Run
US-005 | Runtime Integration | As an operator, settlement rails only go live when QVAC, WDK, compliance, and recipient routes are ready. | Live-money commands are guarded; readiness and launch audit explain missing gates and pass only with complete evidence. | app/live-readiness.js; app/live-launch-audit.js; app/settlement-service.js | npm run check: live readiness, launch audit, settlement-service tests passed. | Run readiness/audit with demo config and live-ready config; verify blocking reasons and pass report match expected gates. | P0 | Integrated | Not Run |  | None | Not Run
US-006 | Runtime Integration | As a developer, the Kawaii app consumes the same tested WDK/QVAC modules as the app runtime. | Staged design modules match the advanced runtime surfaces for core, adapters, worker, settlement, QVAC referee, and Tether WDK bridge. | app/*.js; design/kawaii-app/*.js; commit 84044b3 | Merged commit 84044b3; npm run check passed; Kawaii syntax sweep passed. | Compare staged module files and run app plus audit checks; verify no stale runtime surfaces remain in design/kawaii-app. | P0 | Integrated | Passed (Smoke) |  | None | Not Run | Head during workbook generation: 84044b3.
US-007 | Profile | As a new player, I can choose a username. | Username input updates local state, respects max length, and save falls back to a friendly default when blank. | design/kawaii-app/index.html: #usernameInput, #saveProfile; design/kawaii-app/app.js: bindEvents, renderProfile | UI code inventoried; requires manual form pass. | Enter a long username, save, reload, then save an empty username; verify chip and profile text update safely. | P1 | Integrated | Not Run |  | None | Not Run
US-008 | Profile | As a fan, I can pick my country/team and see it reflected in my avatar and UI. | Team grid selection updates country, kit, avatar portrait/fallback, profile chip, and country-affinity labels. | design/kawaii-app/app.js: renderTeams, avatarSvg, avatarPortrait, renderProfile | UI code inventoried; requires manual selection pass. | Pick several countries, verify active state, avatar art, profile chip, and home/watch/game labels update. | P1 | Integrated | Not Run |  | None | Not Run
US-009 | Profile | As a player, I can save my profile and enter the main Home screen. | Save persists username/team and routes to Home with a toast/status response. | design/kawaii-app/app.js: saveProfile listener, setView, showToast | UI code inventoried; requires manual save pass. | Choose team and username, click Enter, verify Home is active and profile chip reflects saved identity. | P1 | Integrated | Not Run |  | None | Not Run
US-010 | Profile | As a player, I can switch PearCup themes. | First-run picker and theme button apply available themes without losing profile, wallet, or picks. | design/kawaii-app/app.js: THEMES, applyTheme, setTheme, showThemePicker, renderThemeSwitcher | UI code inventoried; requires manual theme pass. | Open theme picker, choose each theme, reload, verify CSS variables and saved state persist. | P2 | Integrated | Not Run |  | None | Not Run
US-011 | Wallet | As a player, I can see my demo wallet balance everywhere I need it. | Wallet chip and wallet management panel show current balance, pending payouts, and ledger lines consistently. | design/kawaii-app/index.html: #walletChip, #walletManage; design/kawaii-app/app.js: renderWalletChip, renderWalletManage | Browser smoke confirmed wallet panel exists; requires wallet behavior pass. | Open Profile wallet panel, compare chip and panel balance before/after funding, pool entry, and game stake. | P1 | Integrated | Not Run |  | None | Not Run
US-012 | Wallet | As a player, I can fund my demo wallet. | Funding buttons increase balance, create ledger entries, and refresh dependent affordability states. | design/kawaii-app/app.js: fundWallet, renderWalletManage, renderPools | UI code inventoried; requires manual wallet pass. | Click each funding amount; verify balance, ledger, bracket affordability, and no duplicate event errors. | P1 | Integrated | Not Run |  | None | Not Run
US-013 | Wallet | As a winner, I can collect pending payouts into my balance. | Collect moves pending payout to wallet balance, clears pending amount, and records ledger history. | design/kawaii-app/app.js: collectPayouts, renderWalletManage | UI code inventoried; requires payout scenario. | Create a win/payout state, click Collect, verify balance, pending payout, and ledger line. | P1 | Integrated | Not Run |  | None | Not Run
US-014 | Wallet | As a player, I am blocked from staking when my balance is too low. | Pool entry or staked game attempts with insufficient funds are blocked with a clear route to funding. | design/kawaii-app/app.js: debitWallet, enterSelectedPool, showStakeConfirm | UI code inventoried; requires negative wallet pass. | Set low balance, try paid pool and paid AI challenge; verify no debit and clear funding feedback. | P0 | Integrated | Not Run |  | None | Not Run
US-015 | Live Data Settings | As an operator, I can configure a live match data source. | Live settings save enabled flag, provider, API key, match id, proxy URL, and poll interval without exposing secrets unnecessarily. | design/kawaii-app/app.js: renderLiveDataSettings, save/test listeners | UI code inventoried; requires settings pass. | Edit all live data fields, save, reload, and verify displayed settings and redaction behavior. | P1 | Integrated | Not Run |  | None | Not Run
US-016 | Live Data Settings | As an operator, I can test the live API connection. | Test button reports success or a readable error and does not break the simulated feed fallback. | design/kawaii-app/app.js: apiRequest, createApiLiveFeed, live settings test handler | UI code inventoried; requires API/fallback pass. | Test with blank, bad, and known-good local proxy settings; verify error/success messaging and fallback. | P2 | Integrated | Not Run |  | None | Not Run
US-017 | Home | As a fan, I can see the current match headline and live state on Home. | Hero shows teams, flags, score, clock/status, room count, and activity without stale or missing labels. | design/kawaii-app/index.html: hero IDs; design/kawaii-app/app.js: renderHomeHero | Browser smoke confirmed Home expected containers exist. | Open Home, verify hero labels, score, state, clock, and team flags after at least one feed tick. | P1 | Integrated | Not Run |  | None | Not Run
US-018 | Home | As a fan, I can switch live dashboard tabs. | Overview, Stats, Rooms, QVAC, and Pools tabs render the correct panel content and active state. | design/kawaii-app/app.js: renderHomeDashboard, renderLivePanel, liveMenu listeners | UI code inventoried; requires tab pass. | Click each live menu tab, verify content changes and no layout overlap on desktop and mobile widths. | P1 | Integrated | Not Run |  | None | Not Run
US-019 | Home | As a player, I can discover bracket pools from Home. | Pool cards show tier, stake, prize, entrants, affordability, and route to Bracket when selected. | design/kawaii-app/app.js: renderPools, #poolGrid | Browser smoke confirmed #poolGrid exists. | Inspect pool cards at different balances; click a pool CTA; verify Bracket opens with matching selected pool. | P1 | Integrated | Not Run |  | None | Not Run
US-020 | Home | As a fan, I can jump from fixtures to the watch room. | Fixture rail indicates live/upcoming state and opens Watch without losing feed state. | design/kawaii-app/app.js: renderHomeDashboard, fixture buttons data-view=watch | UI code inventoried; requires fixture CTA pass. | Click live fixture CTA from Home; verify Watch screen opens and match data matches the Home hero. | P2 | Integrated | Not Run |  | None | Not Run
US-021 | Home | As a player, I can scan leaderboard and room signal panels. | Leader and signal panels display user/peer/runtime status with no empty or contradictory labels. | design/kawaii-app/index.html: #leaderPanel, #signalPanel; design/kawaii-app/app.js: renderHomeDashboard | Browser smoke confirmed #leaderPanel exists. | Open Home after joining watch/game room; verify leaderboard rows, room signal, and runtime status copy. | P2 | Integrated | Not Run |  | None | Not Run
US-022 | Bracket Pools | As a player, I can choose a bracket pool tier. | Tier selector shows current pool, stake, prize, entrants, affordability, and entered state. | design/kawaii-app/index.html: #bracketPoolSelect; design/kawaii-app/app.js: renderPoolSelect | Browser smoke confirmed selector exists. | Open Bracket, switch each tier, verify prize/stake/entrant/affordability details update. | P1 | Integrated | Not Run |  | None | Not Run
US-023 | Bracket Pools | As a player, I can enter a selected bracket pool. | Entry records an intent/payment through the worker-backed WDK adapter, debits wallet, and shows me in entrants. | design/kawaii-app/app.js: enterSelectedPool, createBracketSettlementWorker, createBracketUiTetherWdkAdapter | npm run check: WDK entry intent and worker pool tests passed. | Fund wallet, select tier, enter pool, verify debit, entrants list, WDK payment/audit panel, and persistence. | P0 | Integrated | Not Run |  | None | Not Run
US-024 | Bracket Pools | As a player, I can see all entrants for my selected pool. | Entrants list includes current user plus demo entrants with team/entry/score details and no duplicate rows. | design/kawaii-app/index.html: #bracketEntrants; design/kawaii-app/app.js: renderBracketEntrants | UI code inventoried; requires entrant pass. | Enter multiple tiers and reload; verify current user appears once in the selected tier and demo entrants remain stable. | P2 | Integrated | Not Run |  | None | Not Run
US-025 | Bracket Board | As a player, I can complete a knockout bracket. | Round of 16, quarterfinal, semifinal, final, and champion slots render with connector lines and clickable teams. | design/kawaii-app/app.js: buildRounds, makeMatch, renderTeamRow, scheduleBracketConnectors | Browser smoke confirmed #bracketBoard exists. | Pick winners through every round; verify downstream slots populate and connector lines stay aligned after resize. | P0 | Integrated | Not Run |  | None | Not Run
US-026 | Bracket Board | As a player, if I change an upstream pick, downstream invalid picks are cleared. | Changing an earlier match removes affected downstream picks while preserving unrelated picks. | design/kawaii-app/app.js: getPick, clearDownstream, match-card click handler | UI code inventoried; requires change-pick pass. | Complete bracket, change an R16 pick, verify QF/SF/final dependent picks clear and unrelated branches stay intact. | P0 | Integrated | Not Run |  | None | Not Run
US-027 | Bracket Board | As a player, I can reset my draft picks. | Reset clears draft picks, rerenders the bracket, and does not affect pool entries or wallet ledger. | design/kawaii-app/index.html: #resetPicks; design/kawaii-app/app.js: reset listener | UI code inventoried; requires reset pass. | Make several picks, reset, verify board clears and entry/payment state remains. | P1 | Integrated | Not Run |  | None | Not Run
US-028 | Bracket Board | As a player, I cannot submit an incomplete bracket. | Submit blocks incomplete picks with clear feedback and no settlement/submission event. | design/kawaii-app/index.html: #submitPicks; design/kawaii-app/app.js: submit listener | UI code inventoried; requires negative submit pass. | Submit after only one or two picks; verify error feedback and no submission/audit row is created. | P0 | Integrated | Not Run |  | None | Not Run
US-029 | Bracket Board | As a player, I can submit a completed bracket. | Complete picks lock/record the submission, update entered count/audit panels, and preserve picks after reload. | design/kawaii-app/app.js: submit picks flow, renderEntryLedger, renderBracketStats | npm run check: worker profile/bracket draft and bracket submission signer tests passed. | Complete all picks, submit, reload, verify submitted state, worker evidence, and no signer/route warnings. | P0 | Integrated | Not Run |  | None | Not Run
US-030 | Bracket Settlement | As an operator, bracket pool settlement is auditable through WDK, QVAC, payout, and receipt panels. | Audit accordions display entry intents, confirmations, official result source, QVAC attestation, WDK payout, and settlement receipt. | design/kawaii-app/index.html: #bracketStats, #bracketEntriesPanel, #bracketAudit; app/worker-sim.js | npm run check: trusted pool settlement tests passed. | Enter pool, submit bracket, trigger settlement scenario, inspect all audit accordions and verify receipt fields are populated. | P0 | Integrated | Not Run |  | None | Not Run
US-031 | Bracket Settlement | As a winner, I can provide payout recipient details. | Recipient controls save player route, demo helper fills a route, and WDK payout retries once the route exists. | design/kawaii-app/app.js: renderPayoutRecipients, bindPayoutControls; app/settlement-service.js | npm run check: recipient declaration and retry tests passed. | Attempt payout without recipient, save route, retry settlement, verify recipient evidence and payout route. | P0 | Integrated | Not Run |  | None | Not Run
US-032 | Watch Party | As a fan, I can open a watch room with a live TV surface. | Watch screen shows match title, scorebug, clock, pitch, live board, and stats without empty placeholders. | design/kawaii-app/index.html: #watch, #tvPitch, #tvClock, #tvScore, #tvLiveBoard; app.js: renderWatch | Browser smoke confirmed Watch core elements exist. | Open Watch, wait for feed tick, verify TV surface, scorebug, pitch markers, and stats update. | P1 | Integrated | Not Run |  | None | Not Run
US-033 | Watch Party | As a multilingual fan, I can switch QVAC commentary language. | Language tabs update selected state and commentary feed uses the chosen language or safe fallback translation. | design/kawaii-app/app.js: WATCH_LANGS, COMMENTARY_TEMPLATES, renderCommentaryFeed, languageTabs listener | npm run check: QVAC commentary grounding tests passed. | Switch each language tab while feed is active; verify labels, commentary, and no repeated stale lines. | P2 | Integrated | Not Run |  | None | Not Run
US-034 | Watch Party | As a fan, I receive simulated, relay, or API feed updates in the watch room. | Feed source badge reflects sim/API/relay, and score/stats/commentary update from source-signed events. | design/kawaii-app/app.js: createSimLiveFeed, createApiLiveFeed, live-match.json relay, startLiveFeed | npm run check: source-signed match event and QVAC commentary worker tests passed. | Run with simulation, local relay file, and API settings; verify source badge, stat changes, and commentary updates. | P1 | Integrated | Not Run |  | None | Not Run
US-035 | Watch Party | As a fan, I can chat in the watch room. | Chat form appends local messages, signs/broadcasts room state through watch sync, and survives worker replay checks. | design/kawaii-app/index.html: #chatForm, #chatInput; design/kawaii-app/watch-sync.js | npm run check: worker watch-party ownership and forged event tests passed. | Send chat locally and across two browser windows; verify message order, user label, and no duplicate/forged entries. | P1 | Integrated | Not Run |  | None | Not Run
US-036 | Watch Party | As a fan, I can toggle voice room state. | Voice toggle changes live/muted state, updates room copy, and records worker-owned social state safely. | design/kawaii-app/index.html: #voiceToggle; design/kawaii-app/app.js: voice listener; watch-sync.js | npm run check: watch-party social state tests passed. | Toggle voice on/off; verify button state, participant panel, worker replay state, and reload behavior. | P2 | Integrated | Not Run |  | None | Not Run
US-037 | Watch Party | As a host, I can invite others to the watch room. | Invite/share opens a room share bar or copies a link with a stable room code. | design/kawaii-app/index.html: #shareGameBtn, #roomShareBar; app.js: toggleInviteBar | UI code inventoried; requires clipboard/share pass. | Click invite/share, verify room link appears or clipboard path succeeds, and the UI is reversible. | P2 | Integrated | Not Run |  | None | Not Run
US-038 | Watch Party | As a host, I can share my screen when supported. | Screen share starts/stops in capable browsers and falls back with clear unsupported feedback when media APIs are unavailable. | design/kawaii-app/index.html: #shareScreenBtn, #shareVideo, #shareBadge; app.js: screen share handlers | UI code inventoried; requires permission-aware pass. | Test in supported and unsupported contexts; verify permission prompts are user-controlled and UI state resets after stop. | P2 | Integrated | Not Run |  | None | Not Run
US-039 | Watch Party | As a fan, I can send match reactions. | Reaction buttons animate locally and broadcast through watch sync to peers in the same room. | design/kawaii-app/watch-sync.js: react, bindReactionBar; app.js reaction buttons | UI code inventoried; requires two-client pass. | Open two clients, click reactions, verify both clients show reaction and presence count updates. | P2 | Integrated | Not Run |  | None | Not Run
US-040 | Peer Transport | As a player in browser preview, I can use local P2P fallback transport. | PearCupPeerNet uses BroadcastChannel locally and exposes the same channel contract expected by lobby, watch, and match flows. | design/kawaii-app/peer-net.js; app/transport-sim.js | npm run check: transport-sim and Pear Browser compatibility tests passed. | Open two browser windows, join watch/lobby/game flows, verify messages converge through BroadcastChannel. | P1 | Integrated | Not Run |  | None | Not Run
US-041 | Peer Transport | As a Pear app player, I can use worker-side transport without renderer-only settlement trust. | Peer and settlement events are worker-owned/replay-bound, and staged package keeps SDK runtime out of renderer-only paths. | app/pear-worker.cjs; app/worker-bridge-protocol.js; scripts/pear-browser-compat.mjs | npm run check and audit:pear-browser passed 68 checks. | Run Pear Browser audit and worker preflight; verify no renderer-only WDK/QVAC settlement paths remain. | P0 | Integrated | Passed |  | None | Not Run | Automated gate passed in current checkpoint.
US-042 | Games Lobby | As a player, I can see available Penalty Clash options. | Games lobby renders quick match, paid challenge, friend invite/join, peer list, leaderboard, and audit panels. | design/kawaii-app/index.html: #gameLobby; app.js: renderGameLobby | Browser smoke confirmed Games expected panels exist. | Open Games, verify all lobby actions and panels render at desktop and mobile widths. | P1 | Integrated | Not Run |  | None | Not Run
US-043 | Games Lobby | As a player, I can start a free practice shootout. | Quick match starts against AI without wallet debit, initializes five-round shootout, and focuses aim controls. | design/kawaii-app/app.js: startMatch, ensureShootout, renderShootoutHud | UI code inventoried; requires game interaction pass. | Click quick match, verify balance unchanged, stage visible, round 1 active, and aim zones clickable. | P1 | Integrated | Not Run |  | None | Not Run
US-044 | Games Lobby | As a player, I can accept or cancel a staked AI challenge. | Paid challenge opens confirmation, cancel leaves wallet untouched, accept debits stake and starts match. | design/kawaii-app/app.js: showStakeConfirm, startMatch, debitWallet | UI code inventoried; requires wallet/game pass. | Click paid AI challenge, cancel, then accept after funding; verify wallet, match state, and confirmation copy. | P0 | Integrated | Not Run |  | None | Not Run
US-045 | Games Lobby | As a player, I can invite or join a friend match. | Friend invite creates a room code, join consumes a code, and both clients enter a synchronized peer match. | design/kawaii-app/peer-match.js; design/kawaii-app/peer-lobby.js; app.js invite/join handlers | npm run check: P2P game session lifecycle tests passed. | Open two clients, host friend match, join by code, verify both enter the same game and lifecycle panels update. | P0 | Integrated | Not Run |  | None | Not Run
US-046 | Penalty Clash Gameplay | As a shooter, I can aim and take a penalty kick. | Aim zones and power meter accept input, lock the chosen zone, and resolve a goal/save/miss/post outcome. | design/kawaii-app/app.js: AIM_ZONES, ensureShootoutDom, startAimPhase, kickOutcome, applyKickResult | npm run check: deterministic penalty round tests passed. | Start match, click each aim zone across retries, verify animation, outcome copy, score, and next round behavior. | P0 | Integrated | Not Run |  | None | Not Run
US-047 | Penalty Clash Gameplay | As a player, I can track the shootout score and round state. | HUD shows best-of-five dots, current round, player/AI score, and final result without off-by-one errors. | design/kawaii-app/app.js: SHOOTOUT_TOTAL, renderShootoutHud, endShootout | UI code inventoried; requires full-match pass. | Play through five kicks and early decisive cases; verify HUD, dots, round numbers, and final banner. | P0 | Integrated | Not Run |  | None | Not Run
US-048 | Penalty Clash Gameplay | As a player, I can finish a shootout and choose what to do next. | Final state shows win/loss/draw, prize/refund handling, settlement evidence, Play Again, and Back controls. | design/kawaii-app/app.js: endShootout, play-again/back handlers | UI code inventoried; requires full-match pass. | Finish win, loss, and draw scenarios if possible; verify payout/refund messaging and controls reset safely. | P0 | Integrated | Not Run |  | None | Not Run
US-049 | Penalty Clash Gameplay | As a spectator, I can spectate or start a new shootout safely. | Spectate/New Shootout controls create/reset simulated match state without corrupting wallet, peer state, or audit panels. | design/kawaii-app/index.html: #spectateGame; app.js: spectate/new shootout listeners | UI code inventoried; requires controls pass. | Use Spectate and New Shootout before, during, and after a match; verify state reset and no stale overlays. | P2 | Integrated | Not Run |  | None | Not Run
US-050 | Game Settlement | As a staked player, my game escrow is resolved through QVAC before WDK payout. | Worker creates WDK escrow, records commitments/reveals/state hashes, obtains QVAC attestation, releases/refunds via WDK, and records receipt. | app/worker-sim.js; app/settlement-service.js; design/kawaii-app/app.js: createGameSettlementWorker | npm run check: trusted game settlement and WDK/QVAC release tests passed. | Run a staked game to completion, inspect resolver/audit panels, verify escrow, attestation, payout/refund, and receipt fields. | P0 | Integrated | Not Run |  | None | Not Run
US-051 | Game Settlement | As an operator, settlement disputes fail closed. | Mismatched hashes, forged evidence, wrong winners, missing recipient routes, and invalid QVAC/WDK signatures produce hold/dispute/refund paths instead of payout. | app/worker-sim.test.js; app/qvac-referee.test.js; app/tether-wdk-bridge.test.js | npm run check: forged, mismatched, missing evidence, and dispute tests passed. | Run automated negative tests; manually inspect UI for route-blocked and held settlement messaging where applicable. | P0 | Integrated | Passed |  | None | Not Run | Automated coverage is strong; UI messaging still needs targeted pass.
US-052 | Game Settlement | As a player, I can see game resolver, sync, and replay evidence. | Resolver, tether, runtime, QVAC, sync, and replay panels display event counts, topics, state roots, and receipt status. | design/kawaii-app/index.html: #gameResolver, #tetherPanel, #runtimePanel, #qvacRefPanel, #gameSync, #gameReplay | Browser smoke confirmed panels exist. | Start and finish a game; verify each audit panel updates from empty to evidence-rich state. | P1 | Integrated | Not Run |  | None | Not Run
US-053 | Peer Match | As a peer player, game events converge between two clients. | Signed invites, lifecycle events, choices, reveals, and state hashes replay consistently and reject forged peer events. | app/worker-sim.js; app/transport-sim.js; design/kawaii-app/peer-match.js | npm run check: P2P session lifecycle and forged event tests passed. | Open host and join clients, play several kicks, verify both screens agree and replay panels converge. | P0 | Integrated | Not Run |  | None | Not Run
US-054 | Peer Lobby | As a player, I can discover and challenge peers. | Lobby join announces presence, lists peers, and challenge buttons start shared game codes through PeerMatch. | design/kawaii-app/peer-lobby.js; peer-net.js | UI code inventoried; requires two-client pass. | Open two clients, verify each appears in the other lobby, challenge peer, and confirm both enter shared match. | P1 | Integrated | Not Run |  | None | Not Run
US-055 | Worker Client | As the app, I use the Pear worker bridge when available and local worker otherwise. | Auto worker client detects Pear bridge, caches redacted status, and keeps browser demo fallback synchronous. | app/worker-client.js; app/worker-bridge-protocol.js; app/worker-runtime.js | npm run check: worker-client and bridge protocol tests passed. | Run browser preview and Pear bridge harness; verify bridge preference, fallback, and redacted status behavior. | P0 | Integrated | Passed |  | None | Not Run | Automated coverage passed; Pear runtime manual smoke still recommended.
US-056 | Worker Client | As an operator, worker bridge responses do not leak secrets or full history by default. | Secrets are redacted, WDK seed is not exposed, and event history is opt-in. | app/worker-bridge-protocol.js; app/worker-runtime.js; scripts/pear-browser-compat.mjs | npm run check and Pear Browser audit passed secret/history gates. | Inspect worker status responses with and without includeEvents; verify seeds/secrets are redacted. | P0 | Integrated | Passed |  | None | Not Run
US-057 | Storage and Replay | As the runtime, I keep app, bracket, watch, and game event streams isolated. | Storage namespaces prevent cross-contamination and replay reconstructs the correct state for each flow. | app/storage-sim.js; app/worker-sim.js; design/kawaii-app/storage-sim.js | npm run check: storage-sim and replay-bound worker tests passed. | Create profile, bracket, watch, and game events; inspect namespaces/event logs and replay-derived UI panels. | P0 | Integrated | Passed |  | None | Not Run | Manual UI inspection remains to connect panels to replay evidence.
US-058 | Receipts | As a player, I can trust settlement receipts. | Receipts bind event refs, actors, QVAC attestation, WDK output, and replayed source data. | app/settlement-receipts.js; app/trusted-path-preflight.js | npm run check: settlement receipt verification and trusted-path tests passed. | Generate game and bracket receipts; verify receipt panel fields and independent verification result. | P0 | Integrated | Passed |  | None | Not Run
US-059 | QVAC Referee | As an operator, QVAC attestations require signed referee identity and verified evidence. | Round and pool attestations fail closed unless the review is verified, non-disputed, source-bound, and signed by the referee actor. | app/qvac-referee.js; app/qvac-referee.test.js | npm run check: QVAC attestation verification tests passed. | Run automated tests and inspect UI audit panels for referee signer and attestation status. | P0 | Integrated | Passed |  | None | Not Run
US-060 | QVAC Commentary | As a fan, QVAC commentary is grounded in replayed match events. | Commentary and translations summarize signed/source events and reject peer commentary without QVAC/source grounding. | app/qvac-referee.js; app/worker-sim.js; design/kawaii-app/app.js commentary feed | npm run check: QVAC commentary and peer commentary rejection tests passed. | Watch feed updates, inspect generated commentary language changes, and verify no invented facts appear after source changes. | P1 | Integrated | Not Run |  | None | Not Run
US-061 | Tether WDK | As a staked player, WDK entry and escrow operations bind to signed participants. | Entry intents, confirmations, pending checks, refunds, game escrows, releases, and payouts are signed and replay-verifiable. | app/tether-wdk-bridge.js; app/worker-sim.js; app/settlement-service.js | npm run check: WDK bridge, entry, escrow, payout, refund tests passed. | Run automated suite and inspect UI WDK panels after pool entry and game settlement. | P0 | Integrated | Passed |  | None | Not Run
US-062 | SDK Runtime | As an operator, package SDK adapters can be injected without changing UI flow code. | Runtime package adapters wrap SDK-like QVAC and WDK clients while preserving tested demo adapter behavior. | app/sdk-runtime.js; app/runtime-config.js; app/adapters.js | npm run check: sdk-runtime, adapters, runtime-config tests passed. | Inject SDK-like clients, run preflight, and verify app panels report SDK-backed mode without renderer settlement shortcuts. | P0 | Integrated | Passed |  | None | Not Run
US-063 | Pear Browser Compatibility | As a release owner, I can prove the staged renderer is Pear Browser compatible. | Audit rejects external assets, renderer SDK runtime leakage, missing stage includes, untrusted settlement paths, and missing evidence checks. | scripts/pear-browser-compat.mjs; app/pear-browser-compat.js; design/kawaii-app/pear-browser-compat.js | npm run audit:pear-browser -- --require-pass passed: 68 checks, 0 blocking, 0 warnings. | Run the audit command after every integration and verify 0 blocking and 0 warnings. | P0 | Integrated | Passed |  | None | Not Run
US-064 | Package Staging | As a release owner, staged design assets remain self-contained. | Kawaii app uses local scripts/styles/assets and does not depend on network or unstaged runtime files. | design/kawaii-app/index.html; design/kawaii-app/RELEASE.md; scripts/pear-browser-compat.mjs | Pear Browser audit and syntax sweep passed. | Review script/link tags, run audit, and open app offline/local to verify all assets render. | P0 | Integrated | Passed (Smoke) |  | None | Not Run
US-065 | Responsive UX | As a mobile player, I can use the full app without overlapping controls. | Topbar, dashboard tabs, bracket board, watch room, and game controls remain readable and tappable on narrow screens. | design/kawaii-app/styles.css; app.js resize/scheduleBracketConnectors | Not covered by current automated pass. | Test at mobile and desktop widths; verify text fit, no overlap, and bracket connectors recalculate. | P1 | Integrated | Not Run |  | None | Not Run | This is a likely UX-risk area for the next test loop.
US-066 | Accessibility and Feedback | As a keyboard or screen-reader user, I can understand and operate primary controls. | Buttons have labels, status changes use readable text, controls are focusable, and error/toast copy is understandable. | design/kawaii-app/index.html aria labels; app.js showToast/status copy | Not covered by current automated pass. | Keyboard-tab primary flows, inspect names for icon buttons, and verify toast/status text after errors and successes. | P2 | Integrated | Not Run |  | None | Not Run
US-067 | Error Handling | As a player, failures are explained without trapping me. | Boot, API, wallet, settlement, screen-share, and peer failures show actionable messages and allow retry/recovery. | design/kawaii-app/app.js: error hook, showToast, API/live settings, settlement guards | Browser smoke found no errors; negative states require manual pass. | Trigger bad API, insufficient funds, incomplete bracket, unsupported screen share, and settlement route block; verify recovery. | P1 | Integrated | Not Run |  | None | Not Run
US-068 | Security and Integrity | As an operator, forged or orphaned peer settlement artifacts cannot affect payout state. | Worker rejects forged envelopes, orphaned payouts/releases/receipts, wrong signer bindings, and missing replay dependencies. | app/worker-sim.test.js; app/settlement-receipts.test.js; scripts/pear-browser-compat.mjs | npm run check includes forged/orphaned/resealed peer artifact rejection tests. | Run automated suite; manually inspect audit panels after peer merge scenarios if available. | P0 | Integrated | Passed |  | None | Not Run
US-069 | Launch Readiness | As an operator, I can run preflight checks before launch. | Preflight scripts report trusted path readiness, SDK/worker readiness, live config, and launch audit status. | scripts/preflight-sdk.mjs; scripts/preflight-worker-runtime.mjs; scripts/preflight-trusted-path.mjs; scripts/live-readiness.mjs | npm run check validates preflight/audit modules with node --check and tests where available. | Run all preflight scripts for demo and live config; verify output is actionable and does not claim readiness falsely. | P0 | Integrated | Not Run |  | None | Not Run
US-070 | Release Baseline | As the team, we can prove the integrated branch is clean and tested. | Worktree is clean after integration commit, repo check passes, Kawaii syntax passes, and browser smoke passes. | git status; npm run check; design/kawaii-app syntax sweep; in-app browser at 127.0.0.1:4175 | 2026-07-02 checkpoint: main ahead 1, clean; npm run check passed; Kawaii syntax passed; browser smoke passed. | Run git status, npm run check, Kawaii syntax sweep, and browser top-nav smoke after any fix. | P0 | Integrated | Passed |  | None | Not Run | Use this row as the release gate before/after the full user-story test loop.

## Defect Log
Defect ID | Story ID | Area | Severity | Status | Found In | Summary | Steps | Expected | Actual | Owner | Fix Commit | Retest Status | Notes

## Test Runs
Run ID | Date | Tester | Scope | Command / Scenario | Result | Evidence | Stories Covered | Notes
TR-001 | 2026-07-02 | Codex | Runtime and settlement modules | npm run check | Passed | 282/282 node tests passed; node --check passed for app and scripts; Pear audit included. | US-004, US-005, US-023, US-030, US-031, US-041, US-050 to US-063, US-068 to US-070 | Executed after merge commit 84044b3.
TR-002 | 2026-07-02 | Codex | Pear Browser compatibility gate | npm run audit:pear-browser -- --require-pass | Passed | 68 passed, 0 blocking, 0 warnings. | US-041, US-063, US-064, US-070 | Also executed as part of npm run check.
TR-003 | 2026-07-02 | Codex | Kawaii staged bundle syntax | find design/kawaii-app -maxdepth 1 -type f ( -name '*.js' -o -name '*.cjs' ) -exec node --check {} + | Passed | All staged Kawaii JS/CJS files parsed successfully. | US-001, US-006, US-064, US-070
TR-004 | 2026-07-02 | Codex | In-app browser smoke | Reload http://127.0.0.1:4175/ and click top-nav Profile/Home/Bracket/Watch/Games | Passed | All top-nav buttons were unique, all screens activated, expected panels existed, no boot banner, no console errors. | US-001, US-002, US-006, US-017, US-022, US-032, US-042, US-052, US-070 | Server: python3 -m http.server 4175 --bind 127.0.0.1 --directory design/kawaii-app.

## Source Map
Area | Primary Source | Runtime / UI Surface | Coverage Evidence | Open Manual Focus
Boot and Navigation | design/kawaii-app/index.html; design/kawaii-app/app.js | Shell, nav, state boot, runtime module loading | Browser smoke; node syntax | Persistence and negative boot states
Profile | design/kawaii-app/app.js: renderProfile, renderTeams, avatar helpers | Username, team, avatar, profile chip | Inventoried from code | Full profile save/reload pass
Wallet | design/kawaii-app/app.js: wallet helpers | Balance, funding, payouts, insufficient funds | Inventoried from code | Funding/debit/payout scenarios
Home | design/kawaii-app/app.js: renderHomeHero, renderHomeDashboard | Hero, live tabs, pools, fixture rail, leaders | Browser smoke for containers | All tab content and responsive scan
Bracket Pools | design/kawaii-app/app.js: pool and bracket functions | Pool entry, picks, submissions, WDK/QVAC audit | Runtime tests for worker settlement | Manual pick/reset/submit/audit pass
Watch Party | design/kawaii-app/app.js; watch-sync.js; peer-net.js | TV surface, feed, commentary, chat, voice, share, reactions | Worker social state tests | Two-client sync and screen-share pass
Penalty Clash | design/kawaii-app/app.js; peer-match.js; peer-lobby.js | Lobby, AI match, friend match, aim grid, shootout HUD | Worker/P2P game tests | Full gameplay and two-client pass
Settlement | app/worker-sim.js; settlement-service.js; settlement-receipts.js | Escrow, QVAC, WDK, receipts, disputes, replay | 282 passing tests | UI audit panel evidence pass
QVAC | app/qvac-referee.js; sdk-runtime.js | Referee attestation and commentary | QVAC tests and Pear audit | Live commentary and UI signer display
Tether WDK | app/tether-wdk-bridge.js; worker-sim.js | Entry intents, escrows, payouts, refunds | WDK bridge and worker tests | Manual wallet/audit verification
Peer/Worker Runtime | app/worker-client.js; worker-runtime.js; worker-bridge-protocol.js | Bridge detection, redaction, replay, Pear worker | Worker client/bridge tests and Pear audit | Pear runtime smoke
Release Baseline | package.json scripts; scripts/pear-browser-compat.mjs | npm run check, audit, syntax, browser smoke | All passed on 2026-07-02 | Repeat after every fix